## Sheet1
Site Name | Province | Area | Technology | Technicians required | Travel | Accommodation + LOA (check company ) | Schedule | existing devices | address | Assigned BN | PPPOE username | Password | Sim no. | Router/RN SN | CPE SN | AP SN | Status
Chloorkop | Gauteng | Ekurhuleni | Tarana FWB | Full Team | Vehicle (normal site trip expense) | 20Km's between sites | 2026-02-11 |  | 3430 Successor St, Phomolong |  | CT-UNJ-006@circletel.co.za | CT-UNJ-006 |  | S150F2224001002 | HHU0AENHM6W | G1U52HL002532 | Activated
Alexandra | Gauteng | Johannesburg | Tarana FWB | Full Team | Vehicle (normal site trip expense) |  | 2026-02-11 | already configed (Source connection change) | 47 Third St, Wynberg | X4672-BN-45 | CT-UNJ-002@circletel.co.za | CT-UNJ-002 |  | S150F2224000967 | On site devices | On site devices | Activated
Cosmo City | Gauteng | Johannesburg | Tarana FWB | Full Team | Vehicle (normal site trip expense) | 27Km's between | 2026-02-12 |  | 35 Massachussets Cres | X6582-BN-45 | CT-UNJ-007@circletel.co.za | CT-UNJ-007 |  | S150F2224000981 |  |  | Activated
Fleurhof | Gauteng | Johannesburg | Tarana FWB | Full Team | Vehicle (normal site trip expense) |  | 2026-02-12 |  | Ext 26, Cnr Lavender &, Drumstick St, Fleurhof | X0064-BN-315/X7615-BN-135 | CT-UNJ-008@circletel.co.za | CT-UNJ-008 |  | S150F2224000953 |  |  | Activated #ticket to connect cameras completed
Sky City | Gauteng | Klipwater | Tarana FWB | Full Team | Vehicle (normal site trip expense) | 12Km's between sites | 2026-02-13 |  | 22 Heidelberg Rd, Garthdale AH | X10706-BN-225 | CT-UNJ-009@circletel.co.za | CT-UNJ-009 |  | S150F2224000963 |  |  | Activated #ticket about connection being down resolved
Sicelo | Gauteng | Meyerton | 5G/LTE/FWA | One technician | Vehicle (normal site trip expense) |  | 2026-02-16 |  |  |  | CT-UNJ-011@circletel.co.za | CT-UNJ-011 | 11349663644 | X100PRO862378060205728 | HJX0AXQMS2H |  | Activated / Sim card swapped out , up and running ( MTN to install booster once processed)
Heidelberg | Gauteng | Heidelberg | Tarana FWB | Full Team | Vehicle (normal site trip expense) |  | 2026-02-16 |  | Unnamed Road, Military Base, Heidelberg , heidelberg mall | X6837-BN-45 | CT-UNJ-012@circletel.co.za | CT-UNJ-012 |  | S150F2224001003 |  | G1U52HL044518 | Activated
Tokoza | Gauteng | Ekurhuleni | Tarana FWB | Full Team | Vehicle (normal site trip expense) |  | 2026-02-18 |  | 263 Khumalo St, Thokoza, | X0339-BN-3/X339-BN-135 | CT-UNJ-010@circletel.co.za | CT-UNJ-010 |  | S150F2224000983 | HJX0AV8GD3S | G1U52HL044467 | Activated
Soshanguve (Block P) | Gauteng | Pretoria | Tarana FWB | Full Team | Vehicle (normal site trip expense) |  | 2026-02-25 |  |  |  | CT-UNJ-025@circletel.co.za | CT-UNJ-025 |  | S150F2224000982 | HFK0AKVRRRHY | G1UQ9C8001073 | Activated
Barcelona | Gauteng | Springs | LTE/5G | One technician | Vehicle (normal site trip expense) |  | 2026-02-26 | already configed (Source connection change) |  |  | CT-UNJ-013@circletel.co.za | CT-UNJ-013 | 11349665995 | X100PRO862378061530132 | HKF0AJ3TTVN2 | G1UQ9C800686A | Activated / Intermitent signal issues causing drops to our AP , exploring options to rectify service (attending this week)
Lens ext 10 | Gauteng | Johannesburg | Tarana FWB | Full Team | Vehicle (normal site trip expense) |  | 2026-02-26 |  | 22 Karasberg St, Lenasia South, Lenasia, 1835 | X3555-BN-45 | CT-UNJ-016@circletel.co.za | CT-UNJ-016 |  | S150F2224000947 | HKF0AVA0QMN | G1U9QC8001191 | Activated #ticket about connection attended , stable
Oukasie | North West | Brits | 5G/LTE/FWA | Full Team | Vehicle (normal site trip expense) |  | 2026-02-27 |  | Oukasie sports grounds, Oukasie, Brits | X11752-BN-135 | CT-UNJ-014@circletel.co.za | CT-UNJ-014 | 11349666019 | X100PRO862378060803159 | HJX0AQBM0X1 | G1U52HL044564 | Activated , up and running
Nokaneng | Limpopo | Greater Tubatse | LTE Uncapped | One technician | Vehicle (312KM's from JHB) | 312Km (accomodation required) | 2026-03-02 |  |  |  | CT-UNJ-017@circletel.co.za | CT-UNJ-017 | 11349665979 | X100PRO862378060745004 | HKE0AX32N2D | G1UQ9C800083B | Activated
Phoenix (27 km to durban clinic) | KwaZulu-Natal | Durban | Tarana FWB | Full Team | Vehicle (584 KM's From JHB ) | 584Km accomodation required | 2026-03-03 |  | 28 Corkbrook Cl, Brookdale, Phoenix |  | CT-UNJ-021@circletel.co.za | CT-UNJ-021 |  | S150F2224000952 | HKF0AJRM11S | G1UQ9C8000942 | (hardward issue on site being investigated Poe injector/ RN issue - stock sent down scheduled to attend this week
Sweetwaters | KwaZulu-Natal | Pietermaritzburg | LTE/5G | One technician / Team | Vehicle (site trip from accomodation) | (KZN teams to assist) accomodation required | 2026-03-03 |  |  |  | CT-UNJ-020@circletel.co.za | CT-UNJ-020 | 11349665961 | X100PRO862378061527104 | HKF0AWGHQHW | G1UQ9CB00789A | Activated , issues onsite resolved
New Hanover | KwaZulu-Natal | New Hanover | LTE/5G | One technician / Team | Vehicle (site trip from accomodation) | (KZN teams to assist) accomodation required | 2026-03-04 |  |  |  | CT-UNJ-023@circletel.co.za | CT-UNJ-023 | 11349665987 | X100PRO862378061530355 |  |  | Activated
Jabulani | Gauteng | Soweto | 5G/LTE/FWA | One technician | Vehicle (normal site trip expense) |  | 2026-03-06 |  |  |  | CT-UNJ-015@circletel.co.za | CT-UNJ-015 | 11349666027 | X100PRO862378060760458 | HJX0AYBREXA | G1UQ9C8000921 | Activated
Durban | KwaZulu-Natal | Durban | LTE | One technician / Team | Vehicle (site trip from accomodation) | 27km accomodation required | 2026-03-07 |  | 135 Anton Lembede str , durban |  | CT-UNJ-022@circletel.co.za | CT-UNJ-022 |  |  |  |  | Activated
Zamdela | Free state | Sasolburg | 5G/LTE/FWA | One technician | Vehicle (normal site trip expense) |  | 2026-03-09 |  |  |  | CT-UNJ-019@circletel.co.za | CT-UNJ-019 | 11349666035 | X100PRO86237806817050 | HJX0AHYGXH7 | G1UQ9C800113B | Activated
Kayamandi | Western Cape | Stellenbosch | 5G/LTE | One technician | Vehicle (normal site trip expense) | (WC team to attend) | 2026-03-13 |  |  |  | CT-UNJ-018@circletel.co.za | CT-UNJ-018 |  |  |  |  | Activated
Umsinga | KwaZulu-Natal | Tugela Ferry | LTE/5G | One technician / Team | Vehicle (site trip from accomodation) | (KZN teams to assist) accomodation required | 2026-03-11 |  |  |  | CT-UNJ-024@circletel.co.za | CT-UNJ-024 | 11349666050 | X100PRO862378061405509 | HKE0AN9CZJV | G1UQ9C8000984 | Activated
Collect boards
[5 empty] | # | Account Number | Site Name | Province | PPPoE Username |  | Technology
[5 empty] | 1 | CT-UNJ-001 | Unjani Clinic - Soweto (Diepkloof) | Gauteng | CT-UNJ-001@circletel.co.za |  | -
[5 empty] | 2 | CT-UNJ-002 | Unjani Clinic - Alexandra | Gauteng | CT-UNJ-002@circletel.co.za |  | -
[5 empty] | 3 | CT-UNJ-003 | Unjani Clinic - Khayelitsha | Western Cape | CT-UNJ-003@circletel.co.za |  | -
[5 empty] | 4 | CT-UNJ-004 | Unjani Clinic - Mamelodi | Gauteng | CT-UNJ-004@circletel.co.za |  | -
[5 empty] | 5 | CT-UNJ-005 | Unjani Clinic - Umlazi | KwaZulu-Natal | CT-UNJ-005@circletel.co.za |  | -
[5 empty] | 6 | CT-UNJ-006 | Unjani Clinic - Chloorkop | Gauteng | CT-UNJ-006@circletel.co.za |  | Tarana FWB
[5 empty] | 7 | CT-UNJ-007 | Unjani Clinic - Cosmo City | Gauteng | CT-UNJ-007@circletel.co.za |  | Tarana FWB
[5 empty] | 8 | CT-UNJ-008 | Unjani Clinic - Fleurhof | Gauteng | CT-UNJ-008@circletel.co.za |  | Tarana FWB
[5 empty] | 9 | CT-UNJ-009 | Unjani Clinic - Sky City | Gauteng | CT-UNJ-009@circletel.co.za |  | Tarana FWB
[5 empty] | 10 | CT-UNJ-010 | Unjani Clinic - Tokoza | Gauteng | CT-UNJ-010@circletel.co.za |  | Tarana FWB
[5 empty] | 11 | CT-UNJ-011 | Unjani Clinic - Sicelo | Gauteng | CT-UNJ-011@circletel.co.za |  | 5G/LTE/FWA
[5 empty] | 12 | CT-UNJ-012 | Unjani Clinic - Heidelberg | Gauteng | CT-UNJ-012@circletel.co.za |  | Tarana FWB
[5 empty] | 13 | CT-UNJ-013 | Unjani Clinic - Barcelona | Gauteng | CT-UNJ-013@circletel.co.za |  | LTE/5G
[5 empty] | 14 | CT-UNJ-014 | Unjani Clinic - Oukasie | North West | CT-UNJ-014@circletel.co.za |  | Tarana FWB
[5 empty] | 15 | CT-UNJ-015 | Unjani Clinic - Jabulani | Gauteng | CT-UNJ-015@circletel.co.za |  | 5G/LTE/FWA
[5 empty] | 16 | CT-UNJ-016 | Unjani Clinic - Lens ext 10 | Gauteng | CT-UNJ-016@circletel.co.za |  | Tarana FWB
[5 empty] | 17 | CT-UNJ-017 | Unjani Clinic - Nokaneng | Limpopo | CT-UNJ-017@circletel.co.za |  | LTE Uncapped
[5 empty] | 18 | CT-UNJ-018 | Unjani Clinic - Kayamandi | Western Cape | CT-UNJ-018@circletel.co.za |  | 5G/LTE
[5 empty] | 19 | CT-UNJ-019 | Unjani Clinic - Zamdela | Free State | CT-UNJ-019@circletel.co.za |  | 5G/LTE/FWA
[5 empty] | 20 | CT-UNJ-020 | Unjani Clinic - Sweetwaters | KwaZulu-Natal | CT-UNJ-020@circletel.co.za |  | LTE/5G
[5 empty] | 21 | CT-UNJ-021 | Unjani Clinic - Phoenix | KwaZulu-Natal | CT-UNJ-021@circletel.co.za |  | Tarana FWB
[5 empty] | 22 | CT-UNJ-022 | Unjani Clinic - Durban | KwaZulu-Natal | CT-UNJ-022@circletel.co.za |  | LTE
[5 empty] | 23 | CT-UNJ-023 | Unjani Clinic - New Hanover | KwaZulu-Natal | CT-UNJ-023@circletel.co.za |  | LTE/5G
[5 empty] | 24 | CT-UNJ-024 | Unjani Clinic - Umsinga | KwaZulu-Natal | CT-UNJ-024@circletel.co.za |  | LTE/5G
[5 empty] | 25 | CT-UNJ-025 | Unjani Clinic - Soshanguve (Block P) | Gauteng | CT-UNJ-025@circletel.co.za |  | Tarana FWB